## Summary
Roomly: Production Readiness
Audit date: 2026-10-10. Edit Status / Owner / Target date on the Issues sheet; counts below update automatically.
Severity | Meaning | Total | Open | In progress | Done | % done
Blocker | Store rejection, security hole or data loss. Must fix before launch.
High | Fix before launch or it breaks as you grow.
Medium | Needed for a multi-country, large-scale product.
Low | Cleanup.
Total
Suggested order
1. Security fix: B1 (about a day).
2. Store blockers: B2-B11. Start the 14-day Google Play closed test now so it runs in parallel.
3. Scale: H1-H5, H7, H9 (balance snapshots, pagination, indexes, push worker, pg_cron, staging + Supabase CLI).
4. Growth: Medium items, depending on launch markets.
Effort key: S = under 1 day, M = 1-3 days, L = 1+ week (rough estimates).

## Issues
ID | Severity | Category | Issue | Details | Location | Impact | Recommended fix | Effort | Status | Owner | Target date | Notes
B1 | Blocker | Security | Notification functions callable by any client | notify_household and send_push_for_notification were created after the 'revoke execute from anon' in 0004 and never had permissions locked down; Postgres grants EXECUTE to PUBLIC by default. ensure_period also lacks a household membership check. | supabase/migrations/0016_push.sql:108-191; 0011_apply_fixes.sql:24 | Anyone with the public key and a household ID can insert fake notifications and push arbitrary text to every phone in that household; signed-in users can create period rows in other households. | Revoke EXECUTE on all functions from public/anon/authenticated, grant back only RPCs the app calls; ALTER DEFAULT PRIVILEGES so new functions start closed; add membership check to ensure_period. | S | Open
B2 | Blocker | Store compliance | No in-app account deletion | Settings only has Export and Sign out. No delete-account RPC or Edge Function; remove_member is owner-removes-member, not self-deletion. | src/app/(app)/settings.tsx; account-edit.tsx | Automatic rejection: Apple guideline 5.1.1(v) and Google Play account deletion policy. | Add Delete Account screen + Edge Function (service role) that deletes auth.users row and scrubs/anonymises personal data; add web URL for Play's deletion form. | M | Open
B3 | Blocker | Legal / Store compliance | No privacy policy, terms or support URL | No privacy/terms links anywhere in the app; no consent text on register. No hosted policy page. | src/app/register.tsx; settings.tsx | Both stores require a privacy policy URL; Apple requires a support URL. Data Safety form (Play) and App Privacy labels (Apple) must be filled. | Host privacy policy, terms, support page; link from register and Account; complete Data Safety and App Privacy questionnaires. | S | Open
B4 | Blocker | Branding / Store | App icon is the Expo template logo | assets/images/icon.png and assets/expo.icon are stock Expo; adaptive icon background is template default; display name is lowercase 'roomly'. | assets/images/icon.png; assets/expo.icon; app.json | Rejection or app looks like a test build. | Design real icon set (1024 iOS, adaptive Android fg/bg/monochrome), splash; set name to 'Roomly'. | S | Open
B5 | Blocker | Build / Release | EAS cloud builds crash on launch (no env vars) | EXPO_PUBLIC_SUPABASE_* exist only in local .env (gitignored); eas.json has no env; supabase.ts throws if missing. | eas.json; src/lib/supabase.ts:10 | Every cloud build crashes on start. | Create EAS environment variables per environment (development/preview/production). | S | Done |  |  | EAS production env vars set and verified 2026-10-10. Add to preview env before preview builds.
B6 | Blocker | Store compliance (iOS) | Missing iOS privacy manifest | No ios.privacyManifests in app.json. AsyncStorage, SQLite and file system use Apple 'required reason' APIs. | app.json | App Store upload flagged/rejected. | Add ios.privacyManifests with NSPrivacyAccessedAPITypes (UserDefaults, FileTimestamp, etc.) and collected data types. | S | Open
B7 | Blocker | Infrastructure | Supabase built-in email limits | Default Supabase SMTP sends only a few emails per hour and is not meant for production. | Supabase dashboard > Auth > SMTP | Sign-up confirmations and password resets silently fail once real users arrive. | Configure custom SMTP (Resend, AWS SES, Postmark) with SPF/DKIM on your domain; brand email templates. | S | Open
B8 | Blocker | Infrastructure | Supabase plan / backups | Free projects pause after inactivity and have no point-in-time recovery. Only backup today is in-app CSV export. | Supabase project | Downtime and unrecoverable loss of a financial ledger. | Move to Pro plan, enable PITR, and run a test restore on a schedule. | S | Open
B9 | Blocker | Observability | No crash reporting and no error boundaries | No Sentry/Bugsnag; no ErrorBoundary export in any layout; only two __DEV__ console.warn calls. | src/app/_layout.tsx; package.json | A single render error closes the app and you never find out. | Add Sentry (@sentry/react-native) with source maps uploaded from EAS; root + per-route ErrorBoundary. | S | Open
B10 | Blocker | Store process (Android) | Google Play closed-testing requirement | New personal developer accounts must run a closed test with 12+ testers for 14 consecutive days before production access. | Play Console | Cannot publish publicly until the test is complete. | Start the closed test now, in parallel with other fixes. | S | Open
B11 | Blocker | Store process (iOS) | App Review demo account | Every screen requires sign-in and a household. | App Store Connect | Reviewer cannot use the app, so it is rejected. | Provide a ready demo account with seeded household data and a second member; keep it alive. | S | Open
H1 | High | Scalability | Balances recompute from full history on every read | member_balances / member_ledger re-add a household's entire history every time; no snapshot for closed months. | supabase/migrations/0024_one_balance_expression.sql:61-153 | Each household gets slower every month; DB CPU grows with total data. | Store a balance snapshot per closed period and sum only open months on top. | M | Open
H2 | High | Scalability / UX | No pagination | History loads fixed 200, search loads 500 and filters on device; settlements and pairwise screens load everything. Older history unreachable. | history.tsx:30; search.tsx:18; queries.ts:599,1052 | Slow screens, high data usage, missing history for long-lived households. | Cursor pagination with useInfiniteQuery + .range(); server-side search (trigram/FTS). | M | Open
H3 | High | Performance | Every live update refetches every query | Realtime handler and sync call invalidateQueries() with no filter. | src/lib/realtime.ts:74; src/lib/sync.tsx | Each change makes every open device refetch everything; DB load multiplies with users. | Invalidate only affected query keys based on event kind. | S | Open
H4 | High | Database | Missing indexes | No index on settlements(from_member), (to_member), (period_id); notification_reads(member_id); audit_log(household_id, created_at); push_tokens(token); pending_changes, join_requests, invites; several unindexed FKs. | supabase/migrations | Full table scans on hot paths as data grows. | Add migration with indexes; wrap RLS helper calls as (select current_household()). | S | Open
H5 | High | Push notifications | Push is fire-and-forget | Single net.http_post from trigger; errors swallowed; no retry; no 100-message chunking; DeviceNotRegistered tokens never cleaned; rupee sign hardcoded. | supabase/migrations/0016_push.sql:150 | Lost notifications, invisible failures, growing dead-token list. | Queue table + worker (pg_cron or Edge Function) with batching, retries, receipt checks and token cleanup. | M | Open
H6 | High | Push / Privacy | Sign-out does not unregister push token | unregister_push_token RPC exists but nothing calls it. | src/lib/session.tsx:313 | Signed-out phone keeps receiving the household's notifications. | Call unregister_push_token before signOut. | S | Open
H7 | High | Backend jobs | Recurring expenses only post when someone opens the app | No pg_cron schedule; posting triggered from home screen; failures swallowed. | src/app/(app)/(tabs)/index.tsx:157; 0030 | Rent/bills post late; notifications delayed. | Schedule post_due_recurrences with pg_cron daily; log failures. | S | Open
H8 | High | Security / Abuse | No rate limiting or input limits | Invite codes 6 chars via random() (not cryptographically secure), brute-forceable; preview_invite leaks household name; no CAPTCHA on sign-up; no text length caps; no max amount; unvalidated currency code. | supabase/migrations/0004_functions.sql:86-157; schema | Household takeover attempts, spam accounts, oversized data, overflow in formatting. | gen_random_bytes codes (8+ chars), attempt throttling table, Supabase CAPTCHA (hCaptcha/Turnstile), CHECK constraints on lengths and amounts. | M | Open
H9 | High | DevOps | Single environment, manual migrations | One Supabase project; migrations pasted into SQL Editor with no record of what is applied. | supabase/; .env.example | Untested changes hit production; drift between environments. | Adopt Supabase CLI (config.toml, supabase db push); separate staging and production projects. | M | Open
H10 | High | Release | Test builds receive production OTA updates | preview profile uses channel 'production'; app.json hardcodes expo-channel-name header. | eas.json; app.json | Testing updates reach real users, or vice versa. | Separate preview/production channels; remove hardcoded request header. | S | Open
H11 | High | Build | Android size settings only in local android/ folder | arm64-only, minify, shrinkResources set by hand; android/ is gitignored, so EAS builds lose them. | scripts/rebuild-native.mjs | EAS APK/AAB ~3x larger. | Move settings to expo-build-properties plugin (note: Play AAB handles ABI splits automatically). | S | Open
H12 | High | DevOps | No CI pipeline | No .github/workflows or EAS workflows; lint/typecheck/tests run manually. | repo root | Regressions ship unnoticed. | GitHub Actions: lint, typecheck, npm test on every PR; EAS build on main. | S | Open
H13 | High | Security (client) | Auth tokens in plain AsyncStorage | Supabase session persisted to AsyncStorage instead of secure storage. | src/lib/supabase.ts:16 | Tokens readable on rooted/jailbroken devices or from backups. | Use expo-secure-store adapter (chunked, since sessions exceed 2KB) or encrypted storage. | S | Open
H14 | High | Privacy / Data | Personal data retained after user deletion; unbounded growth | Deleting auth user only nulls members.user_id; names and emails in join_requests remain. audit_log stores full JSON forever; notifications grow forever. | 0001_schema.sql:33; 0021_audit_config_tables.sql | Privacy-law non-compliance; storage growth. | Anonymise on deletion; retention policy / partitioning for audit_log and notifications. | M | Open
M1 | Medium | Internationalization | India-only currency and locale | INR, en-IN, rupee symbol and 'GPay' hardcoded; formatting ignores households.currency; database timezone set to Asia/Kolkata. | src/lib/money.ts:23-49; dates.ts:41; 0030:88 | Wrong output for any non-Indian household. | Format with household currency; keep DB in UTC; let owners set household timezone. | M | Open
M2 | Medium | Internationalization | No translations | All UI strings hardcoded English; no expo-localization or i18n library. | src/ | Limits markets. | Extract strings to i18n (i18next / lingui) with expo-localization. | L | Open
M3 | Medium | Deep linking | Only roomly:// scheme links | No associatedDomains / Android intentFilters; invites are typed codes, not links. | app.json; forgot-password.tsx | Reset links fail on desktop and some mail apps; harder invites. | Add https Universal Links / App Links and shareable invite URLs. | M | Open
M4 | Medium | Release | No forced update or feature flags | No minimum-version gate; 0022 already broke older builds once. | src/lib/build-info.ts | Cannot block an outdated build after a breaking migration. | Server-side min_version config checked on launch; feature flag table or service. | S | Open
M5 | Medium | Offline | Only 'add expense' works offline | Edits and settlements need network; offline detected by regex on error text; outbox not scoped per user. | src/lib/outbox.ts; sync.tsx:50 | Poor experience on flaky networks. | Queue edits/settlements; use expo-network state; scope outbox per user. | M | Open
M6 | Medium | Accessibility | Thin accessibility support | 57 labels across ~35 screens; settings rows and sign-out lack roles; large-font layout untested. | src/ | Excludes users; accessibility complaints. | Label all controls, test VoiceOver/TalkBack and 200% font scale, verify contrast. | M | Open
M7 | Medium | Product | No product analytics | No analytics SDK. | package.json | Cannot measure activation, retention or funnels. | Add PostHog / Amplitude with privacy-respecting events; disclose in privacy labels. | S | Open
M8 | Medium | Support | No support, FAQ or rate-app prompt | More menu has none; no expo-store-review. | src/app/(app)/(tabs)/more.tsx | Users cannot reach you; fewer store ratings. | Add Help/FAQ, contact email, in-app review prompt after positive moments. | S | Open
M9 | Medium | Push UX | Permission asked immediately; taps do nothing | OS prompt shown with no explanation; no notification response handler. | src/lib/push.ts:129 | More denials; tapping a push does not open the item. | Pre-permission explainer screen; route on notification tap using data.kind/entityId. | S | Open
M10 | Medium | Testing | No end-to-end UI tests | Only domain/structure/security tests plus manual checklist; no Maestro/Detox, no component tests. | tests/ | Key flows regress unnoticed. | Maestro flows for sign-up, add expense, settle, close month; run in CI on EAS builds. | M | Open
M11 | Medium | Performance | Long lists rendered in ScrollView | Home is one ScrollView with ~14 .map() calls; settle.tsx (1080 lines), recurring, reports similar. | src/app/(app)/(tabs)/index.tsx:290-768; settle.tsx | Slow rendering for large households. | Use FlatList/FlashList; split large screens into components. | M | Open
L1 | Low | Cleanup | Template leftovers | reset-project.js and npm script; unused react-logo / expo-badge / tutorial-web images; unused deps (react-hook-form, @expo/ui, expo-glass-effect; verify expo-symbols, expo-web-browser first). | scripts/; assets/images; package.json | Bundle size and confusion. | Remove unused files and dependencies. | S | Open
L2 | Low | Scope | Web target undecided | web.output configured and react-native-web/react-dom installed, but no web-specific product work. | app.json; package.json | Extra surface to test and maintain. | Decide: ship web properly or remove it. | S | Open
L3 | Low | Release | Build number mismatch | extra.buildNumber is 9, iOS buildNumber / Android versionCode are 10. | app.json | Wrong version shown in app. | Use EAS remote versioning with autoIncrement. | S | Open
L4 | Low | Legal | LICENSE names Expo as copyright holder | MIT template copyright '650 Industries (Expo)'. | LICENSE | Incorrect ownership claim. | Replace with your own license or delete if closed-source. | S | Open
L5 | Low | Docs | Supabase README out of date | Migration table stops at 0027; repo has 0001-0033. | supabase/README.md:21 | Setup confusion. | Update table (or replace with CLI-based instructions). | S | Open
L6 | Low | UX copy | Developer text visible to users | Message says 'See PUSH-SETUP.md'. | src/lib/push.ts:110 | Unprofessional. | Replace with user-friendly copy. | S | Open

## What We Have
Area | What exists | State
Authentication | Email/password sign-up, email confirmation, password reset (PKCE), session auto-refresh | Working
Households | Create, invite codes, join approval, ownership handover, away periods, member admin | Working
Expenses | Equal/custom splits, categories, edit history, void/undo, search | Working
Recurring expenses | Idempotent posting, missed-month backfill (12 months), day 1-31 | Working
Settlements | Pairwise balances, suggested payments, payee confirms payment | Working
Monthly close | Closed months locked, enforced in DB | Working
Reports | Charts by category and member, month statements | Working
Export / backup | CSV export via share sheet | Working
Offline | Durable outbox for new expenses with idempotent server writes; persisted query cache (7 days) | Working (partial)
Notifications | In-app feed with unread badge, live updates via Supabase Realtime | Working
Push | Token registration, Android channel, server send via pg_net | Working (needs hardening)
Security | Row-level security on all 18 tables; balances derived, never stored; period derived server-side | Working (see B1)
Money correctness | Integer paise; split balance trigger; ledger_imbalance canary | Working
UI | Dark mode, onboarding, empty states, custom UI kit | Working
Updates | expo-updates OTA, runtime version policy, manual check in Settings | Working
Build | EAS profiles (preview APK, production AAB), build-stamp script | Working
Tests | Domain, structure and security tests (~2,200 lines) + manual test plan + SQL smoke tests | Working
Code hygiene | No console.log, no TODO/FIXME | Clean

## Not In App
Area | Feature | Notes | Decision
Monetization | Subscriptions / in-app purchases (RevenueCat) | Decide business model before launch | Undecided
Social sign-in | Google and Apple sign-in | If Google is added, Sign in with Apple becomes mandatory on iOS | Undecided
Receipts | Receipt photo capture and storage | Needs camera/photos permission strings and Storage bucket with RLS | Undecided
Payments | UPI / payment app deep links to settle | Common expectation in India | Undecided
Multi-currency | Multiple currencies within one household, FX | Ties to M1 | Undecided
Tablet | iPad / Android tablet layouts | supportsTablet is false | Undecided
Widgets | Home-screen widgets (balance at a glance) | Optional growth feature | Undecided
Admin console | Internal support/admin tool | Needed to help users at scale | Undecided
Moderation | Abuse reporting, block, account lock | Needed with open sign-up | Undecided
Monitoring | Uptime, DB metrics, alerting (e.g. on ledger_imbalance) | Operational must-have | Undecided
Legal | India DPDP Act 2023 compliance; GDPR if EU users | Consent, data requests, grievance officer | Undecided
Store assets | Screenshots, descriptions, feature graphic, keywords | Required for listings | Undecided

## Legend
How to use
Light-yellow cells are for you to edit: Status, Owner, Target date, Notes (Issues) and Decision (Not In App).
Status options: Open, In progress, Done, Won't fix. Done rows turn green and struck through.
Summary counts and % done are formulas driven by the Issues sheet.
Severity: Blocker = store rejection / security / data loss; High = breaks at scale; Medium = needed for growth; Low = cleanup.
Effort: S < 1 day, M 1-3 days, L 1+ week. Rough estimates from the 2026-10-10 code audit.
Locations are paths in the roomly repo, with line numbers where known.